## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Kareem | 2024-03-27 | 2024-03-27 | 8 | 8
Create Date dimension | All | 2024-03-27 | 2024-03-27 | 8 | 8
Create Demographic dimension | Kareem/Khaled | 2024-03-27 | 2024-03-27 | 8 | 8
Create Education dimension | Diego | 2024-03-27 | 2024-03-27 | 8 | 8
Create Fact Table | Kareem | 2024-03-27 | 2024-03-27 | 8 | 8
Create Industry Dimension | Kareem/Khaled | 2024-03-27 | 2024-03-27 | 8 | 8
Create Labour Force Dimension | Diego | 2024-03-27 | 2024-03-27 | 8 | 8
Staging Date dimension | All | 2024-03-27 | 2024-03-27 | 8 | 8
Staging Demographic dimension | All | 2024-03-27 | 2024-03-27 | 8 | 8
Staging Education dimension | Kareem | 2024-03-27 | 2024-03-27 | 8 | 8
Staging Labour dimension | Diego | 2024-03-27 | 2024-03-27 | 8 | 8
Staging Industry dimension | Khaled | 2024-03-27 | 2024-03-27 | 8 | 8
Surrogate key pipeline | Kareem | 2024-03-27 | 2024-03-27 | 8 | 8
Staging of fact table – including FKs and measures | Kareem | 2024-03-27 | 2024-03-27 | 8 | 8
Data quality handling and reporting | Khaled/Diego | 2024-03-27 | 2024-03-27 | 8 | 8
Creating high level data staging plan | All | 2024-03-27 | 2024-03-27 | 8 | 8
|  | 2024-03-27 | 2024-03-27 | 8 | 8