## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing |  |  |  | 20 | 18
Data summarisation | Kareem | 2024-04-09 | 2024-04-09 | 10 | 9
.. Visualisation of attributes | Kareem | 2024-04-09 | 2024-04-09
Data transformation | Khalid/Diego | 2024-04-09 | 2024-04-09 | 10 | 9
.. Missing values | Khalid/Diego | 2024-04-09 | 2024-04-09
.. Categorical data | Khalid/Diego | 2024-04-09 | 2024-04-09
.. Numeric data | Khalid/Khalid | 2024-04-09 | 2024-04-09
.. Feature selection
Data mining - Classification
Decision tree
Gradient Boosting
Random Forests
Comparison of results
Summary
Anomaly detection |  |  |  | 5 | 5
One-class SVM | Kareem | 2024-04-09 | 2024-04-09
Summary | Kareem | 2024-04-09 | 2024-04-09
Other tasks - please specify